## Pre-Migration Checklist
MVGM VvE Beheer - Pre-Migration Checklist
Migration: mvgm.com to mvgm-vvebeheer.nl
Category | Task | Owner | Due Date | Status | Notes
Benchmark | Export current keyword rankings for VvE terms | SEO Team | Before Phase 1 | Completed | Focus on vve beheer + city terms
Benchmark | Screenshot Google Analytics traffic data (30 days) | SEO Team | Before Phase 1 | Not Started | Document organic sessions
Benchmark | Run site:mvgm.com/nl/vastgoeddiensten/vve-beheer | SEO Team | Before Phase 1 | Not Started | Count indexed pages
Benchmark | Save GSC backlink data export | SEO Team | Before Phase 1 | Completed | Done - 114 backlinks identified
New Site | Verify all destination URLs return 200 | Dev Team | Before Phase 1 | Not Started | Test all 113 target URLs
New Site | Confirm canonical tags point to new domain | Dev Team | Before Phase 1 | Not Started | No canonicals to mvgm.com
New Site | Check no pages have noindex | Dev Team | Before Phase 1 | Not Started | All VvE pages must be indexable
New Site | Create XML sitemap | Dev Team | Before Phase 1 | Not Started | mvgm-vvebeheer.nl/sitemap.xml
New Site | Verify robots.txt allows crawling | Dev Team | Before Phase 1 | Not Started
New Site | Confirm HTTPS/SSL certificate working | Dev Team | Before Phase 1 | Not Started
New Site | Test mobile-friendliness | Dev Team | Before Phase 1 | Not Started | Google Mobile-Friendly Test
GSC Setup | Add mvgm-vvebeheer.nl as new property | SEO Team | Before Phase 1 | Not Started
GSC Setup | Verify ownership (DNS or HTML) | SEO Team | Before Phase 1 | Not Started
GSC Setup | Submit sitemap to GSC | SEO Team | Before Phase 1 | Not Started
Redirects | Test redirect rules on staging | Dev Team | Before each phase | Not Started | No chains, no loops
Redirects | Backup server config before each phase | Dev Team | Before each phase | Not Started | For rollback if needed
Content | Verify /contact/ page exists (8 backlinks) | Content Team | Before Phase 2 | Not Started | CRITICAL - missing from original
Content | Verify /faq/ page exists | Content Team | Before Phase 2 | Not Started | 2 backlinks to FAQ
Content | Verify all city pages exist on new site | Content Team | Before Phase 3 | Not Started | 30 city/region pages

## Phase Timeline
Migration Phase Timeline
Phase | Date | Action | URLs | Owner | Priority | Status
Phase 1 | 09-02-2026 | Legal pages (privacy, cookie, disclaimer) | 3 | Ronald | High | Pending
Phase 1 | 09-02-2026 | Contact & service pages | 2 | Ronald | High | Pending
Phase 1 | 09-02-2026 | News articles (VvE related) | 13 | Ronald | Low | Pending
Phase 1 | 10-02-2026 | Monitor Phase 1 - check GSC for errors | - | SEO Team | High | Pending
Phase 2 | 16-02-2026 | VvE Homepage (43 backlinks - CRITICAL) | 1 | Brightlot | Critical | Pending
Phase 2 | 16-02-2026 | Contact form page (8 backlinks) | 1 | Ronald | Critical | Pending
Phase 2 | 16-02-2026 | Package pages (Premium, Plus, Start, etc.) | 7 | Ronald | Critical | Pending
Phase 2 | 16-02-2026 | Offerte/quote pages | 7 | Ronald | Critical | Pending
Phase 2 | 16-02-2026 | Customer service pages | 4 | Ronald | High | Pending
Phase 2 | 16-02-2026 | FAQ pages | 3 | Ronald | Medium | Pending
Phase 2 | 16-02-2026 | Team/about pages | 2 | Ronald | Medium | Pending
Phase 2 | 17-02-2026 | Request indexing in GSC for key pages | - | SEO Team | High | Pending
Phase 2 | 17-02-2026 | Monitor Phase 2 - check for 404s | - | SEO Team | High | Pending
Phase 3 | 23-02-2026 | City pages (Amsterdam, Rotterdam, etc.) | 30 | Ronald | High | Pending
Phase 3 | 23-02-2026 | Region pages (Noord-West, Zuid-Oost, etc.) | 8 | Ronald | High | Pending
Phase 3 | 23-02-2026 | Sustainability/ESG pages | 2 | Ronald | Medium | Pending
Phase 3 | 23-02-2026 | Newbuild VvE pages | 2 | Ronald | Medium | Pending
Phase 3 | 24-02-2026 | Update mvgm.com internal links | - | Brightlot | High | Pending
Phase 3 | 24-02-2026 | Update footer/navigation links | - | Brightlot | Medium | Pending
Post | 01-03-2026 | Week 1 performance review | - | SEO Team | High | Pending
Post | 15-03-2026 | Month 1 performance review | - | SEO Team | Medium | Pending
Post | 01-06-2026 | Full recovery assessment (3 months) | - | SEO Team | Medium | Pending

## Link Equity Rules
Link Equity Preservation Rules
Rule | Do | Do Not | Why It Matters
Redirect Type | Always use 301 (permanent) | Never use 302 (temporary) | 301 passes 90-99% link equity; 302 passes minimal
Redirect Chains | Direct redirect: A to C | Chain redirect: A to B to C | Each hop loses ~10% equity
Content Match | Match topic: /vve-premium/ to /pakket/premium/ | Generic: /vve-premium/ to / | Topical relevance transfers ranking signals
URL Structure | Preserve semantics: /amsterdam/ to /amsterdam/ | Change meaning: /amsterdam/ to /cities/ | Google recognizes semantic similarity
Redirect Duration | Keep redirects active 12+ months | Remove after a few weeks | Google needs time to process all redirects
Trailing Slashes | Handle both: /page and /page/ | Only redirect one variant | Users/links may use either format
Query Parameters | Map specific params to new URLs | Ignore query string redirects | Preserves conversion tracking links
Canonical Tags | Point to new domain only | Mix old/new domain canonicals | Conflicting signals confuse Google
Internal Links | Update to point directly to new URLs | Rely only on redirects | Direct links pass more equity than redirects
HTTPS | Redirect to HTTPS on new domain | Allow HTTP access | Security signals affect rankings

## Monitoring Schedule
Post-Migration Monitoring Schedule
Period | Check | Tool | Target | Actual | Status
Week 1 (Daily) | Crawl errors | GSC - Coverage | 0 new errors |  | Pending
Week 1 (Daily) | 404 errors | GSC - Coverage - Excluded | <5 new 404s |  | Pending
Week 1 (Daily) | New pages indexed | site:mvgm-vvebeheer.nl | Pages appearing |  | Pending
Week 1 (Daily) | Traffic drop | Google Analytics | <20% drop (normal) |  | Pending
Week 1 (Daily) | Server errors | Server logs | 0 500 errors |  | Pending
Week 2-4 (Weekly) | Ranking positions | Semrush/Ahrefs | Stabilizing |  | Pending
Week 2-4 (Weekly) | Organic traffic | Google Analytics | Recovering |  | Pending
Week 2-4 (Weekly) | Backlinks appearing | GSC - Links | New domain showing |  | Pending
Week 2-4 (Weekly) | Redirect errors | Screaming Frog | 0 chain/loops |  | Pending
Month 2-3 | Full traffic recovery | Google Analytics | >=90% of pre-migration |  | Pending
Month 2-3 | Ranking recovery | Rank tracker | Same or improved |  | Pending
Month 2-3 | Old URLs de-indexed | site:mvgm.com vve-beheer | Decreasing count |  | Pending
Month 2-3 | Conversion recovery | Google Analytics | >=90% of pre-migration |  | Pending

## Common Mistakes
Common Migration Mistakes to Avoid
Mistake | Problem | Solution | How to Check
Soft 404s | Page returns 200 but shows error content | Ensure all destinations have real content | Manual check + Screaming Frog
Wrong Canonical | New page canonical points to old domain | Update all canonicals to mvgm-vvebeheer.nl | View source, check link rel canonical
Mixed HTTP/HTTPS | Internal links use http instead of https | Audit all internal links, ensure HTTPS | Screaming Frog protocol report
Blocking Googlebot | robots.txt blocks crawling or noindex tags | Check robots.txt and meta robots before go-live | GSC URL Inspection tool
Forgetting Internal Links | mvgm.com still links to old VvE URLs | Update internal links to new domain directly | Crawl mvgm.com, check for old URLs
Using 302 Instead of 301 | 302 passes minimal link equity | Always use 301 for permanent moves | curl -I [url] to check response code
Redirect Chains | A to B to C loses equity at each hop | All redirects go directly to final URL | Redirect checker tool
Not Monitoring | Issues go unnoticed for weeks | Set calendar reminders for checks | GSC email alerts for crawl errors
Removing Redirects Too Soon | Old backlinks stop working | Keep redirects active 12+ months | Do not remove from server config
Missing Query Params | URLs with ?parameters return 404 | Map all query string variations | Check GSC for 404s with params
No Rollback Plan | Cannot recover if something breaks | Backup config before each phase | Test rollback on staging first
Skipping Benchmarks | Cannot measure success/failure | Document traffic and rankings before | Export reports before Phase 1

## Success Metrics
Migration Success Metrics
Metric | Acceptable | Good | Excellent | Your Result
Traffic Recovery (3 months) | 80% | 90% | 100%+
Ranking Recovery (3 months) | -5 positions | Same | Improved
Crawl Errors | <10 | <5 | 0
404 Errors | <20 | <10 | 0
Redirect Chains | <5 | 1-2 | 0
Indexing Speed (weeks) | 4-6 | 2-3 | 1
Conversion Recovery | 80% | 90% | 100%+
Backlink Transfer | 80% | 90% | 95%+

## pre-migration-indexedpages
URL | Last crawled | Source: GSC
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/leiden/ | 2026-01-20
https://mvgm.com/nl/vve-beheer-veelgestelde-vragen/ | 2026-01-20
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/team-schade/ | 2026-01-20
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/eindhoven/ | 2026-01-20
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/den-haag-rijswijk/ | 2026-01-19
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/mvgm-vve-regio-zuid-west/ | 2026-01-19
https://mvgm.com/nl/vastgoeddiensten/compacte-vve-pakketten/ | 2026-01-19
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/dordrecht/ | 2026-01-19
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/limmen/ | 2026-01-19
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/leeuwarden/ | 2026-01-19
https://mvgm.com/nl/mvgm-vve-biedt-trainees-een-veelzijdige-kick-start-van-hun-carriere-in-het-vastgoed/ | 2026-01-19
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/rijnmond/ | 2026-01-19
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/enschede/ | 2026-01-18
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/verduurzaming/ | 2026-01-18
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/mvgm-vve-regio-noord-oost/ | 2026-01-18
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/managementteam-mvgm-vve/ | 2026-01-18
https://mvgm.com/nl/vastgoedtypes/commercial-real-estate/vve-commercieel/ | 2026-01-18
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/den-haag/ | 2026-01-18
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/den-bosch/ | 2026-01-18
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/amsterdam/ | 2026-01-17
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/vve-whatsapp/ | 2026-01-17
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/groningen/ | 2026-01-17
https://mvgm.com/nl/mvgm-vve-in-middelburg-nu-ook-lokaal-aanwezig-middelburg/ | 2026-01-17
https://mvgm.com/nl/mvgm-vve-nu-ook-lokaal-aanwezig-in-utrecht/ | 2026-01-17
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/contactformulier-vve/ | 2026-01-17
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/breda/ | 2026-01-17
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/extra-producten/ | 2026-01-17
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/automatische-incasso/ | 2026-01-17
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/offerte-aanvraag/ | 2026-01-16
https://mvgm.com/nl/vastgoeddiensten/commercieel-vastgoedmanagement/retail/winkel-vve-beheer/ | 2026-01-16
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/zwolle/ | 2026-01-16
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/team-service-support-data/ | 2026-01-15
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/almere/ | 2026-01-15
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/mvgm-vve-regio-midden-west/ | 2026-01-15
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/het-customer-care-team/ | 2026-01-15
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/arnhem/ | 2026-01-15
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/tilburg/ | 2026-01-15
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/team-finance-financiele-administratie/ | 2026-01-15
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/mvgm-vve-regio-noord-west/ | 2026-01-15
https://mvgm.com/nl/vve-beheer/vve-beheer-voor-nieuwbouwprojecten/ | 2026-01-15
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/lelystad/ | 2026-01-14
https://mvgm.com/nl/mvgm-vve-lanceert-nieuwe-beheerpakketten-en-biedt-hiermee-altijd-een-pakket-aan-die-het-beste-bij-de-wensen-van-een-vve-past/ | 2026-01-14
https://mvgm.com/nl/passend-vve-beheer/ | 2026-01-13
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/amersfoort/ | 2026-01-13
https://mvgm.com/wp-content/uploads/2022/11/branchevoorwaarden-vgm-nl-mvgm-vve.pdf | 2026-01-13
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/beurs/ | 2026-01-13
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/team-kwaliteit-innovatie/ | 2026-01-13
https://mvgm.com/nl/mvgm-neemt-het-vve-beheer-van-ruijters-vastgoed-over/ | 2026-01-13
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/apeldoorn/ | 2026-01-13
https://mvgm.com/nl/mvgm-neemt-actys-wonen-en-actys-vve/ | 2026-01-12
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/zeeland/ | 2026-01-12
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/verduurzaming/stappenplan-verduurzamen-van-uw-vve/ | 2026-01-12
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/mvgm-vve-regio-midden-oost/ | 2026-01-11
https://mvgm.com/nl/uitdaging-oprichten-nieuwbouw-vve/ | 2026-01-11
https://mvgm.com/nl/opstarten-nieuwbouw-vve/ | 2026-01-11
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/deventer/ | 2026-01-10
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/nijmegen/ | 2026-01-10
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/emmen/ | 2026-01-10
https://mvgm.com/vve-faq/ik-wil-mijn-vve-bijdrage-automatisch-laten-incasseren/antwoord-ik-wil-mijn-vve-bijdrage-automatisch-laten-incasseren/ | 2026-01-10
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/utrecht/ | 2026-01-09
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/mvgm-vve-regio-zuid-oost/ | 2026-01-09
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/ | 2026-01-09
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/maastricht/ | 2026-01-09
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/rotterdam/ | 2026-01-09
https://mvgm.com/nl/mvgm-neemt-vve-beheer-van-marsaki-over/ | 2026-01-08
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/team-bankzaken-crediteuren/ | 2026-01-08
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/ik-ben-al-klant-mijn-vve/ | 2026-01-08
https://mvgm.com/nl/efficienter-overzichtelijker-vve-beheer-overstap-naar-softwarepakket-twinq/ | 2026-01-07
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/assen/ | 2026-01-06
https://mvgm.com/nl/mvgm-vve-behaalt-opnieuw-het-prestigieuze-skg-ikob-certificaat/ | 2026-01-04
https://mvgm.com/nl/stappenplan-nieuwbouw-vve/ | 2026-01-02
https://mvgm.com/nl/mvgm-kondigt-samenwerking-vvemanager-aan/ | 2025-12-28
https://mvgm.com/nl/wet-verbetering-functioneren-vve-voor-kleine-vves-wat-te-doen/ | 2025-12-28
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/offerte-aanvragen-vastgoedtaxaties/ | 2025-12-28
https://mvgm.com/nl/mvgm-vve-op-de-vve-beurs-haaglanden/ | 2025-12-27
https://mvgm.com/vve-faq/ik-wil-mijn-automatisch-incasso-stopzetten/ | 2025-12-27
https://mvgm.com/nl/mvgm-vve-lanceert-nieuwe-missie-en-visie/ | 2025-12-27
https://mvgm.com/nl/mvgm-vve-start-digitaal-vergaderen/ | 2025-12-27
https://mvgm.com/nl/mvgm-verbetert-dienstverlening-voor-winkel-vves/ | 2025-12-27
https://mvgm.com/nl/aanneemovereenkomst-mvgm-vve/ | 2025-12-24
https://mvgm.com/vve-faq/ik-wil-mijn-vve-bijdrage-automatisch-laten-incasseren/ | 2025-11-30
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/bedankt-voor-uw-interesse/ | 2025-11-11

## premigration refering links
Target page | Incoming links | Linking sites | Source: GSC
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/ | 43 | 14
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/contactformulier-vve/ | 8 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/amsterdam/ | 6 | 2
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/breda/ | 5 | 4
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/den-haag-rijswijk/ | 4 | 2
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/ik-ben-al-klant-mijn-vve/ | 4 | 2
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/offerte-aanvraag/ | 4 | 2
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/almere/ | 3 | 1
https://mvgm.com/nl/mvgm-neemt-actys-wonen-en-actys-vve/ | 2 | 2
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/automatische-incasso/ | 2 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/den-bosch/ | 2 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/den-haag/ | 2 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/eindhoven/ | 2 | 2
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/groningen/ | 2 | 2
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/rotterdam/ | 2 | 2
https://mvgm.com/nl/vve-beheer-veelgestelde-vragen/ | 2 | 2
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/arnhem/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/enschede/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/limmen/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/maastricht/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/managementteam-mvgm-vve/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/mvgm-vve-regio-zuid-oost/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/mvgm-vve-regio-zuid-west/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/nijmegen/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/utrecht/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/verduurzaming/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/vve-whatsapp/ | 1 | 1
https://mvgm.com/nl/vastgoeddiensten/vve-beheer/zwolle/ | 1 | 1
https://mvgm.com/nl/vastgoedtypes/commercial-real-estate/vve-commercieel/ | 1 | 1